## Slide 1
Start
A
6
E
2
B
3
C
2
F
1
G
6
D
5
End
H
7
I
4
What are the paths to completion and their durations?

## Slide 2
Start
A
6
E
2
B
3
C
2
F
1
G
6
D
5
End
H
7
I
4
Complete the forward pass.

## Slide 3
Start
A
6
E
2
B
3
C
2
F
1
G
6
D
5
End
H
7
I
4
Complete the backward pass.

## Slide 4
Start
A
6
E
2
B
3
C
2
F
1
G
6
D
5
End
H
7
I
4
Expose the float.

## Slide 5
Start
A
6
E
2
B
3
C
2
F
1
G
6
D
5
End
H
7
I
4
What are the paths to completion and their durations?
ABCD = 16
EFGI = 13
EFHI = 14

## Slide 6
Start
A
1
6
6
E
1
2
2
B
7
3
9
C
10
2
11
F
3
1
3
G
4
6
9
D
12
5
16
End
H
4
7
10
I
11
4
14
Complete the forward pass.

## Slide 7
Start
A
1
6
6
1
6
E
1
2
2
3
4
B
7
3
9
7
9
C
10
2
11
10
11
F
3
1
3
5
5
G
4
6
9
7
12
D
12
5
16
12
16
End
H
4
7
10
6
12
I
11
4
14
13
16
Complete the backward pass.
You can finish no later than Day 16, the last day of the critical path.

## Slide 8
Start
A
1
6
6
1
0
6
E
1
2
2
3
2
4
B
7
3
9
7
0
9
C
10
2
11
10
0
11
F
3
1
3
5
2
5
G
4
6
9
7
3
12
D
12
5
16
12
0
16
End
H
4
7
10
6
2
12
I
11
4
14
13
2
16
Expose the float.